## Resource Planning
[18 empty] | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[18 empty] | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029
[7 empty] | P1 GM |  |  |  |  | P1 GM | [5 empty] | 12: KICK OFF; 4: REQF; 6: FFV; 8: EFV; 12: AFV; 9: SSSR; 7: SOP
NEW FILL THIS MANDATORY
[17 empty] | Sum FTE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3.5 | 2.5 | 4 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Status | 7250 |  | 64000
|  |  | FTE ALLOCATION | [14 empty] | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE
Check input | Keywords | Product Constellation | Main_Pillar | Main_Pillar SCAN | DEPARTMENT | PROJECT | PROJECT TO BE CHARGED | P1 / P2 | Workpackage | Sub Disciplines Activity (Task) | Location_PL/GTC | Sub Disciplines | Internal/ External | HCC/LCC | Total Hours | External Resource | Total Cost in EUR (CAA currency) | time axis 2025-08-01 to 2029-12-01
OK | KPI | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | KPI | NON LiDAR_Cairo | SYV-General | Internal | LCC | 350 | no | 4000 | 2026-03-01: 0.5; 2026-04-01: 0.5; 2026-05-01: 0.5; 2026-06-01: 0.5; 2026-07-01: 0.5; 2026-08-01: 0.5; 2026-09-01: 0.5; 2026-10-01: 0.5; 2026-11-01: 0.5; 2026-12-01: 0.5; 2027-01-01: 0.5; 2027-02-01: 0.5; 2027-03-01: 0.5; 2027-04-01: 0.5; 2027-05-01: 0.5; 2027-06-01: 0.5; 2027-07-01: 0.5; 2027-08-01: 0.5; 2027-09-01: 0.5; 2027-10-01: 0.5; 2027-11-01: 0.5; 2027-12-01: 0.5; 2028-01-01: 0.5; 2028-02-01: 0.5
OK | Trace checker | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | Data factory TC | LIDAR_Bietigheim | SYV-General | Internal | HCC | 6000 | no | 35000 | bar: 2027-08-01 to 2028-03-01
no FTE planned | SiL | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | Reprocessing SIL |  | SYV-General | Internal |  |  | no
no FTE planned | HIL | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | Reprocessing HIL |  | SYV-General | Internal |  |  | no
no FTE planned | System Test | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | SYS.5 |  | SYV-General | Internal |  |  | no
no FTE planned | System Integration Test | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | SYS.4 |  | SYV-General | Internal |  |  | no
no FTE planned | Pipeline | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | Data factory Pipeline |  | SYV-General | Internal |  |  | no
no FTE planned | Visualization | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | Visualization |  | SYV-General | Internal |  |  | no
OK | Vehicle tooling | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | Vehicle tooling | NON LiDAR_Prague | SYV-General | Internal | LCC | 150 | no | 25000 | 2027-12-01: 1; 2028-01-01: 2.5; 2028-02-01: 1
no FTE planned | RCC | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | Reprocessing RCC |  | SYV-General | Internal |  |  | no
no FTE planned | Operations | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | Operations |  | SYV-General | Internal |  |  | no
no FTE planned | Operations | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | Operations |  | SYV-General | Internal |  |  | no
no FTE planned | PIL | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | Reprocessing PIL |  | SYV-General | Internal |  |  | no
no FTE planned | Other | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | Other |  | SYV-General | Internal |  |  | no
no FTE planned | SiL | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYS2xx | KPI |  | SYV-General | Internal |  |  | no
no Allocation done | SiL | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P2 BMW | P2 BMW | P2 | 2-SYS2xx |  |  | SYV-General | Internal |  | 750 | no |  | 2027-08-01: 2; 2027-09-01: 2; 2027-10-01: 2; 2027-11-01: 2

## Expenses Proj Spec
[16 empty] | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[16 empty] | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029
[14 empty] | P1 GM |  | 12: KICK OFF; 4: REQF; 6: FFV; 8: EFV; 12: AFV; 9: SSSR; 7: SOP
[14 empty] | Status | 527150
|  |  | Project Specific Expenses | [8 empty] | Input Currency |  | EUR |  | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR | EUR
Check Input | Keywords | Product Constellation | Main_Pillar | Main_Pillar SCAN | DEPARTMENT | PROJECT | PROJECT TO BE CHARGED | P1 / P2 | Workpackage | Location_PL | Expenses Type | Outsourced Workpackage(yes/no) | Deferred payments | Sub Disciplines Activity (Task) | Total Cost in EUR (CAA currency) | time axis 2025-08-01 to 2029-12-01
OK | SiL | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 2-SYSVAL2xx | LIDAR_Bietigheim | Contracted Workpackage | yes | YES_6 months | KPI - Lane detection KPI | 7000 | 2026-01-01: 2000; 2026-04-01: 5000
OK | HIL | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 1-SYSVAL1xx |  | Lincese | no | NO | KPI Analysis License | 215000 | 2026-05-01: 15000; 2026-06-01: 200000
OK | System Test | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 1-SYSVAL1xx |  | Hardware | no | NO | Data Processing Workstation | 5150 | 2027-02-01: 5000; 2027-03-01: 150
OK | System Integration Test | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P1 GM | P1 GM | P1 | 1-SYSVAL1xx | NON LiDAR_Prague | Contracted Workpackage | yes | NO | Server Maintenance Service | 300000 | 2027-02-01: 300000
no Expenses planned | Other | 1 Base | SystemValidation | 6 SystemValidation | SysVal | P2 BMW | P2 BMW | P2 | 4-SYSVAL4xx |  | Travel | no | NO | BMW Travel pass | 0